## Sheet1
Action Item | Date/Value | Days from Today
First Trial Date | 2017-06-09 | 130
Number of Trial Days | 3
Last Trial Date | 2017-06-11 | 132
Opening Date | 2017-03-27 | 56 | Default is eight weeks prior to closing date
Closing Date | 2017-05-22 | 112 | Default is the Monday that is at least two weeks prior to the first trial date
The following are calculated on the above information
Application due to AKC | 2017-01-16 | -14 | Application is due at least 18 weeks before Closing date
Premium to AKC for Review | 2017-02-27 | 28
Premium Distribution | 2017-03-13 | 42 | Premiums are to be sent to the AKC and exhibitors at least two weeks prior to the opening date
Email Reminder one week | 2017-05-15 | 105
Move up deadline | 2017-06-05 | 126
Results to exhibitors | 2017-06-12 | 133
Results to AKC | 2017-06-13 | 134
Formulas:
Days from Today = [Date/Value]-TODAY()
Date/Value = B2+[Date/Value, row above]-1
Date/Value = [Date/Value, row below]-(8*7)